## SCOPE
SN | CN | Candidate Name | Action | Date | Location | Replacements | Actionable | GH | Duration
1 | C1 | Dimple Julyani | Resignation | 2019-02-06 | Chennai | TOD | TOB | Y
2 | C2 | Subhrajit Sahoo | Out | 2018-04-30 | Chennai | TBE till 30 May | Gautam | Y | 69
3 | C3 | Nitesh Raj | Out | 2018-04-30 | Chennai | TBE till 30 May | Gautam | Y | 69
4 | C4 | Manoj Singh | Out | 2018-03-31 | Chennai | Gourav Soni | Gautam | Y | 39
5 | C5 | Lokesh Singh Loha | Continue | 2018-09-30 | Chennai |  |  | Y | 70
6 | C6 | Piyush Pathak | Out | 2018-02-13 | Chennai | Harmeet | Gautam | N | -7
7 | C7 | Pawan Tiwari | Out | 2018-04-30 | Chennai | He is agreed to stay in Chennai as per the new COLA, If performance is not an issue we may propose Vikram to not replace him | Gautam | Y | 69
8 | C8 | Ansuya Prasad Kala | Out | 2018-02-28 | Chennai | TBE till 30 May | Gautam | Y | 8
9 | C9 | C.Rose Mary | Continue | 2018-09-30 | Chennai |  |  | N | 222
10 | C10 | Mohammed Raffi.M | Continue | 2018-04-30 | Chennai |  |  | N | 69
11 | C11 | Sarbeswar Maharana | Out | 2018-04-30 | Chennai | TBE till 30 May | Gautam | Y | 69
12 | C12 | Lokesh Mewara | Continue | 2018-09-30 | Chennai |  |  | Y | 70
13 | C13 | Alaudeen. P | Continue | 2018-09-30 | Chennai |  |  | N | 222
14 | C14 | Reka Ramalingam | Out | 2018-03-31 | Chennai | To discuss with Vikram |  |  | 39
15 | C15 | J P Kiruthiga | Continue | 2018-09-30 | Chennai |  |  |  | 222
16 | C16 | Krishna Kishore Gunta | Out | 2018-03-31 | Chennai |  |  |  | 39
17 | C17 | Sugan K | Continue | 2018-08-30 | Chennai |  |  |  | 191
18 | C18 | Dasari Ashok Chakravarthy | Continue | 2018-08-30 | Chennai
19 | C19 | Ajith Regidi | Out | 2018-03-31 | Chennai
| C20 | Tech Manager
20 | C21 | Solution Architect
21 | C6 | Harmeet Singh | In | TOD | Chennai | Interview need to be schedule with Vikram
| C11 | Namrata Gupta | In | TOD | Chennai | Interview need to be schedule with Vikram
| C2 | Charu Rathi | In | TOD | Chennai | Interview need to be schedule with Vikram, She will be free from AmBank project on 30 april 18 , we are keeping 15 days as buffer so she will be availabe for Scope from 15 may 2018 | Gautam
22 | C23 | Rohit Panchani | To be offered |  | Bangalore | Neet to Check the Status from HR Discussed with HR, Offer is yet to release | BInay
23 | C24 | Gourav Soni | To be offered |  | Chennai | Neet to Check the Status from HR | Binay
24 | C25 | S.Subash Subramanian | Client interview scheduled | 2018-02-14 | Chennai | New dates for client interview | Gautam
25 | C26 | Rakesh Patel | Client interview scheduled | 2018-02-13 | Chennai | New dates for client interview | Gautam
26 | C27 | Viknesh Subramanian | Shortlisted by GIC, Client interview to be scheduled |  | Chennai | New dates for client interview
27 | C28 | Adinarayana Yarram | Client interview scheduled | 2018-02-13 | Chennai | New dates for client interview
28 | C29 | Mahendravarma | Shortlisted by GIC, Client interview to be scheduled |  | Chennai | New dates for client interview
29 | C30 | Shubham Mittal | Shortlisted by GIC, Client interview to be scheduled |  | Chennai | New dates for client interview
30 | C31 | Navneet Singh | Shortlisted by GIC, Client interview to be scheduled |  | Chennai | New dates for client interview
31 | C32 | Siluvai Premildon M | Shortlisted by GIC, Client interview to be scheduled |  | Chennai | New dates for client interview
32 | C33 | Sakshi Shrivastava | Client interview scheduled | 2018-02-13 | Chennai | New dates for client interview
33 | C34 | Avinash Dupaguntla | Client interview scheduled | 2018-02-13 | Chennai | New dates for client interview
34 | C35 | Chinna krishna | Client interview scheduled | 2018-02-14 | Chennai | New dates for client interview
35 | C36 | Yadu Nandan Arora | Client interview scheduled | 2018-02-14 | Bangalore | New dates for client interview
36 | C37 | Praneet Vanakudre | Client interview scheduled | 2018-02-14 | Bangalore | New dates for client interview
Formulas:
Duration = DAYS([Date], TODAY())